## fd2008
Field Day 2013
June 22-23
Task | Resources | Owner
FD Chairperson (recruited by vice president) |  | Tanna, KC0URO
Determine class that W0BU will enter as |  | TCRC board
Repeater Article
Acquire Reservations from park |  | Tanna, KC0URO
Food and other logistics. |  | Tanna, KC0URO
Review Role and Responsibilities for Station Managers
Contact Script
Station Etiquette
Section Chart
Sign-up Sheet
"Special Points" Coordinator
Alternate Power Contacts (5x)
Emergency Communications Visit
NTS Message Handling
Satalite QSO |  | John, W0JT
Alternative Power Points (solar) |  | Dave, KE0NA
W1AW Message Copy |  | Doug, NA0VY
Educational activity bonus
Site visitation from elected official
Site visitation by a representative of an agency
GOTA
Public Location |  | Tanna, KC0URO and TCRC board
Web submission
Media/Communications (pre-event notifications) |  | Dave, KE0NA
Event Photographer(s) |  | Dave, KE0NA/Tanna, KC0URO
Designate simplex frequency for Sat/Sun |  | 145.555
Set-up FD received site
Public Information Table |  | Art, WB0JMG
Prepare sign-in sheets |  | Tanna, KC0URO
Solicit/staff sign-ins |  | station managers
ARRL / Amature Radio Literature
Club Literature
Find and designate station managers for:
Station 1 – 10m, 15m, 20m, 40m, 80m,160m CW |  | Doug, NA0VY
Station 2 – (10m, 15m with approval) 20m, 80m,160m Phone |  | Dave, KE0NA
GOTA - 10m,15m Phone (100w max) 20m,80m PSK (35W max) |  | Art, WB0JMG
VHF/UHF |  | John T. N0JT
Locate radios for the stations.
Station 1 – 10m, 15m, 20m, 40m, 80m,160m CW |  | Doug, NA0VY
Station 2 – (10m, 15m with approval) 20m, 80m,160m Phone |  | Dave, KE0NA
GOTA - 10m,15m Phone (100w max) 20m,80m PSK (35W max) |  | Art, WB0JMG
VHF/UHF |  | John, W0J
Identify lodging for the stations (trailers / tents).
Station 1 – 10m, 15m, 20m, 40m, 80m,160m CW |  | Terrace Oaks West shelter
Station 2 – (10m, 15m with approval) 20m, 80m,160m Phone |  | Art's camper?
GOTA - 10m,15m Phone (100w max) 20m,80m PSK (35W max) |  | Terrace Oaks West shelter
VHF/UHF |  | John's vehicle
Locate antennas for the stations.
Station 1 – 10m, 15m, 20m, 40m, 80m,160m CW |  | gap titan from Jim's house
Station 2 – (10m, 15m with approval) 20m, 80m,160m Phone |  | Art's dipole
GOTA - 10m,15m Phone (100w max) 20m, & PSK @ (35W max) |  | Shawn and Art
GOTA - 40m, 80m | Trap Dipole
VHF/UHF |  | John's antenna set-up
Antenna prep and set up |  | ALL
Transport gap antenna, generator, etc. from Jim's house |  | Jeff, W0KF
Safety Officer
Generator fueling (stand by with fire extinguisher during act)
mark guy lines |  | ALL
Safety briefing |  | ALL
Call a halt for lightning (if needed)
Extinguish fire at end of contest |  | ALL
Traffic control
Power line safety during tower operations |  | ALL
Entertainment
Fire Bowl
Charcoal |  | Tanna, KC0URO or Dave's gas grill?
Computers and Network Setup
Request FD Writelog license key (WØBU)
Logging Server
Locate computers |  | station managers
Station 1 |  | station managers
Station 2 |  | station managers
GOTA |  | station managers
VHF/UHF |  | station managers
Install logging software |  | already installed
Misc Tasks
Set-up tools |  | ALL
Sledge Hammer
Antenna Analyzer |  | Art, WB0JMG, Dave, KE0NA, Jeff, W0KF
Ropes
Coax Adapters
Extra Coax
Extra tower stakes |  | N/A
Generators |  | Craig, KC0DMF
Generators
Generators
station managers
Power cords
FØOD Lightes
Gas
Arrange gas runs
Pack-up and move antennas/towers back to storage location |  | ALL
Prepare report to the board following the event
Prepare and submit the club report to the ARRL